## Cover-JLL
Cairo Gate Project
CONSTRUCTION CONTRACT
Interim Payment Certificate No.06
2026-07-21 | DATE : | [6 empty] | Contract Ref. : PK #49C
Contract Name: Remaining Works for Grand Residence Building G03
Contractor: CONCORDE PLUS
| 2025-12-30 |  | Date of signing LOA | 34863905 |  |  |  | Original Contract Sum | [6 empty] | 0
| 2026-01-02 |  | Commencement Date | 66906203.4424 |  |  |  | Provisional Sums / On Account V.O.'s | 1.9191
Calendar day | 120 |  | Contract Duration | 0 |  |  |  | Approved V.O.'s (Additions)
| 0 |  | Time Extension | 0 |  |  |  | Approved V.O.'s (Omissions)
| 2026-05-02 |  | Date of Completion | 101770108.4424 |  |  |  | Adjusted Contract Sum
|  |  |  | 66906203.4424 |  |  |  | Total Values of CAI's: |  |  | 814967.63
[5 empty] | 2026-07-10 |  |  | WORK DONE & MATERIALS ON SITE AS OF :
17676428.3045 | [7 empty] | Gross Value of Works Executed To End of Invoice Period
31492970.9754 | [7 empty] | Value Work Executed Provisional Sums / On Account V.O.'s To End of Invoice Period |  |  | 814971.367
0 | [7 empty] | Value Work Executed Approved V.O.'s To End of Invoice Period
0 | [7 empty] | Materials On Site To End of Invoice Period
495780.3519 |  |  |  |  | 2026-07-10 |  |  | Payment against Price Adjustment due to Change in Cost up to:
Included |  | Value Added Tax (VAT 14%)
49665179.6318 |  | Sub - Total | [7 empty] | 2769%
ADDITIONS / OMISSIONS
10459171.5 |  |  |  |  | 30% | 10459171.5 | Total Advance Payment |  |  | 35.7982 |  | 2536147
-10459171.5 |  |  |  |  | 30% | -10459171.5 | Less : Recovery to Date (AP)
[6 empty] | 0 |  |  |  | 130000
-2483258.9816 |  |  |  | 5% | 49665179.6318 |  |  | Retention Withheld
-2483258.9816 |  |  |  | 5% | 49665179.6318 |  |  | Performance Security
7026434.1035
-435659.4705 |  |  |  | 1% | 43565947.0454 |  |  | Less Withholding Taxes |  |  | 128809.5
879734.5
-2483258.9816 |  |  |  | 5% | 49665179.6318 |  |  | Less Social Insurances
-496651.7963 |  |  |  | 1% | 49665179.6318 |  |  | Less Labour Force
-148995.5389 |  |  |  | 0.3% | 49665179.6318 |  |  | Egyptian Syndicate of Engineering stamp duties
6171241.7874
-61140.56 | [7 empty] | Back Charge & Withheld Amounts | [5 empty] | 49835000
77.35%
-26586676.8496 | [7 empty] | Previous Payments
14486278.4718 | [7 empty] | NET PAYMENT DUE AGAINST I.P.C. #06 |  | 8190275.3944 | 542681.9728 |  |  | 6176461.0095
[8 empty] | IN WORDS: Only, Fourteen Million, Four Hundred Eighty-Six Thousand, Two Hundred and Seventy-Eight Egyptian Pounds and Forty-Seven Piastres. |  |  | 52962.429 |  | 2571858.3901 |  |  | 41072955.3214
Funds to be Paid to the Contractor .
|  | Approved By : Emaar Misr |  |  |  |  | JLL Misr LLC | Prepared By : |  | 2571858.3901 | 2539509.9762 |  |  | 864374.8143
879735.5
879735.5
| EMAAR Misr Project Director |  |  | EMAAR Misr Cost and Contracts |  | EMAAR Misr Project Manager |  | JLL Misr LLC
ACCEPTED BY THE CONTRACTOR AS FULL
|  |  | AND FINAL SETTLEMENT OF ALL RELATED | [7 empty] | 64767.87
|  |  | AND CONSEQUENTIAL COSTS AND TIME |  |  |  |  | DISTRIBUTION |  |  | 14551046.3418
|  |  | ASSOCIATED WITH THIS PAYMENT CERTIFICATE |  |  |  |  | MD Financial ( Original ) |  |  |  |  | 54170.118
MD Technical
[8 empty] | EMAAR MISR PROJECT DIRECTOR FOR TECHNICAL AFFAIRS |  | 2727072.1653 | 2539509.9762
JLL Misr LLC
Contractor
Contractor
16176872.5646
|  |  |  | 222331.6397 |  |  | 222949.6757 | 222949.6757
| 0.4707 |  | 171765.3082
221817.6704
222949.6757